## Defect Report
Defect ID | Sumamry | Detected By | Defect date | Assign To | Severity | Priority | Status | Build Version | Module | Environment | Defect Type | Reproduce Steps | Expected Result | Acual Resut | Comment
Defect _01 | Privacy Policy' Checkbox field in 'Register Account' page is not marked with red colour * symbol | Purnima | 2025-03-12 |  | Minor | P2(Low) | open | Version 1.1 | Register Account | UAT | Functional | 1. Open the Application URL in any browser 2. Click on 'My Account' Dropmenu 3. Select 'Register' option 4. Check the 'Privacy Policy' checkbox field in the displayed 'Register Account' page | Privacy Policy' check box field should be marked with red colour * symbol | Privacy Policy' check box field is mandatory but not marked with red colour * symbol.
Defect_02 | Password' and 'Password Confirm' fields in 'Register Account' page are accepting simple passwords | Purnima | 2025-03-12 |  | Major | P1(Medium) | open | Version 1.1 | Register Account | UAT | Functional | 1. Open the Application URL in any browser 2. Click on 'My Account' dropmenu 3. Select 'Register' option 4. Enter details into all the mandatory fields 5. Enter simple password say 'abcd' into the 'Password' and 'Password Confirm' fields 6. Select 'Privacy Policy' checkbox field 7. Click on 'Continue' button | Warning message informing the User to enter a password matching the complexity standards should be displayed | Simple password got accepted and there is no warning message regarding the complexity standards of the Password.
Defect_03 | User is getting logged out on clicking Browser back button | Purnima | 2025-03-12 |  | Critical | P1(Medium) | open | Version 1.1 | LOG IN | UAT | Functional | 1. Open Application URL in any browser 2. Click on 'My Account' dropmenu 3. Select 'Login' option 4. Enter valid email address into 'E-Mail Address' field and valid password into 'Password' field 5. Click on 'Login' button 6. Click on browser back button two times | User should not get logged out | User is getting logged out
Defect_04 | User is getting logged in automatically on browsing back immediately after logout | Purnima | 2025-03-12 |  | Major | P1(Medium) | open | Version 1.1 | LOG IN | UAT | Functional | 1. Login to the Application 2. Click on 'My Account' dropmenu 3. Select 'Logout' option 4. Click on browser back button | User should not get logged in automatically | User is getting logged in automatically
Defect_05 | User is not getting logged out in one browser, when logged out in another browser | Purnima | 2025-03-12 |  | Minor | P2(Low) | open | Version 1.1 | LOGOUT | UAT | Functional | 1. Login to the Application with same credentials in Chrome and Firefox Browser 2. Logout in Chrome browser 3. Check performing any action in Firefox browser | User should also get logged out in Firefox browser | User is not getting logged out automatically in Firefox browser
Defect_06 | User is able to reset the password | Purnima | 2025-03-12 |  | Critical | P1(high) | open | Version 1.1 | FORGOT PASSWORD | UAT | Functional | 1. Click on 'Forgotten Password' link from Login page 2. Enter the email address of an existing account for which you have forgot the password 3. Click on 'Continue' button 4. Check the registered email address for which the password got reset 5. Click on the link for resseting the password from the received email body 6. Enter new password into the 'Password' and 'Confirm' fields 7. Click on 'Continue' button 8. Enter the email address into the E-Mail address field and the new resetted password into the 'Password' field 9. Click on 'Login' button | 1. User should be taken to 'Forgotten Password' page 2. Success message with text - 'An email with a confirmation link has been sent your email address.' should be displayed in green color 3. Validate that an email is received regarding resseting of the password to the registered email address 4. User should be taken 'Reset your Password' page 5. Success message with text - 'Success: Your password has been successfully updated.' should be displayed in green color and User should be navigated to 'Login' page 6. User should be able to login with the new password | 1. Application Email system is not working
Defect_07 | user logging into the Application with the old password after resetting it | Purnima | 2025-03-12 |  | Critical | P1(high) | open | Version 1.1 | FORGOT PASSWORD | UAT | Functional | 1. Enter registered email address into the 'E-Mail address' field 2. Enter new password into the 'Password' field 3. Click on 'Login' button | 1. User should not be able to login with old password | 1. Application Email system is not working
Defect_08 | User has given the same password into the 'Password' and 'Confirm' fields of the 'Reset your Password' page | Purnima | 2025-03-12 |  | Critical | P0(high) | open | Version 1.1 | FORGOT PASSWORD | UAT | Functional | 1. Click on 'Forgotten Password' link from Login page 2. Enter the email address of an existing account for which you have forgot the password 3. Click on 'Continue' button 4. Check the registered email address for which the password got reset 5. Click on the link for resseting the password from the received email body 6. Enter a password into the 'Password' field 7. Enter a different password into the 'Confirm' fields 8. Click on 'Continue' button | 1. A field level warning message with text - 'Password and password confirmation do not match!' should be displayed under 'confirm' field | 1. Application Email system is not working
Defect_09 | User resetting the password without giving the new password in the 'Password' and 'Confirm' fields of 'Reset your Password' page | Purnima | 2025-03-12 |  | Critical | P0(high) | open | Version 1.1 | FORGOT PASSWORD | UAT | Functional | 1. Click on the reset password link available in the email 2. Don't enter any password into the 'Password' and 'Confirm' fields of the 'Reset your Password' page 3. Click on 'Continue' button | 1. Field level warning message with text - 'Password must be between 4 and 20 characters!' should be displayed for 'Password' field | 1. Application Email system is not working
Defect_10 | Negative, Null and Zero values are accepted by the Qty field in Product Display Pages | Purnima | 2025-03-12 |  | Minor | P0(High) | open | Version 1.1 | Product display page | UAT | Functional | 1. Open Application URL 2. Enter any Product Name say 'iMac' into the Search box field 3. Click on the button having Search icon 4. Click the Product displayed in the Search results 5. Change the quantity to Negative or Blank or Zero in the Qty field of Product Display Page 6. Click on 'Add to Cart' button | Warning message informing the User to enter a positive quantity into the Qty field should be displayed | Success message with text - Success: You have added Product to your shopping cart! is getting displayed
Defect_11 | $8 is displayed instead of $5 in the displayed 'Estimate Shipping & Taxes' dialog | Purnima | 2025-03-12 |  | Major | P0(High) | open | Version 1.1 | Shopping Cart | UAT | Functional | 1. Open any Application URL 2. Navigate to Shopping Cart page after adding a Product to Cart 3. Click on 'Estimate Shipping & Taxes' dialog 4. Enter Country say 'United States' into the 'Country' text field 5. Enter Region/State say 'California' into the 'Region/State' text field 6. Click on 'Get Quotes' button | $5 should be displayed in the 'Estimate Shipping & Taxes' dialog | For the first time after opening the browser and following the steps to reproduce, $8 is getting displayed in the 'Estimate Shipping & Taxes' dialog
Defect_12 | User can provide future date for the 'Order Date' field while returning the order | Purnima | 2025-03-12 |  | Critical | P1(Medium) | open | Version 1.1 | Product Returns | UAT | Functional | 1. Login to the Account having few orders placed 2. Click on 'Order History' Right column option 3. Click on 'View' icon option of any order displayed in the table of 'Order History' page 4. Enter any future date into the 'Order Date' field in the displayed 'Product Returns' page 5. Provide/Select all the mandatory fields and click on 'Submit' button | Warning message informing the User to provide a valid date should be displayed | Future Date provided in the 'Order Date' field is accepted and return is placed
Defect_13 | Page text is not displayed in the 'About Us', 'Delivery Information', 'Privacy Policy' and 'Terms & Conditions' page | Purnima | 2025-03-12 |  | Minor | P2(Low) | open | Version 1.1 | Affiliate | UAT | Functional | 1. Open Application URL 2. Click on 'About Us' footer option or other footer options like 'Delivery Information', 'Privacy Policy’ and 'Terms & Conditions' page | Proper page text should be displayed in the pages | No page text is getting displayed in the page
Defect_14 | Normal User who has not registered for the Affiliate account is able to login from 'Affiliate Login' section | Purnima | 2025-03-12 |  | Critical | P1(Medium) | open | Version 1.1 | Affiliate | UAT | Functional | 1. Open Application URL 2. Click on 'Affiliate' footer link 3. Login from the 'Affiliate Program' page by providing credentials of the normal User who has not registered for an Affiliate account from the 'Affiliate Login' section 4. Click on 'Login' button | User doesn't have any affiliate account warning message should be displayed | Normal User not registered for affiliate account is able to login
Defect_15 | 'About Us' Footer link | Purnima | 2025-03-12 |  | Critical | P1(Medium) | open | Version 1.1 | Header Menu Footer Options | UAT | Functional | 1. Click on 'About Us' Footer link | User should be taken to 'About Us' page and proper text/information should be displayed on this page | Page Text is not displayed in this page
Defect_16 | Delivery Information' Footer link | Purnima | 2025-03-12 |  | Major | P0(High) | open | Version 1.1 | Header Menu Footer Options | UAT | Functional | 1. Click on 'Delivery Information' Footer link | User should be taken to 'Delivery Information' page and proper text/information should be displayed on this page | Page Text is not displayed in this page
Defect_17 | Privacy Policy' Footer link | Purnima | 2025-03-12 |  | Major | P0(High) | open | Version 1.1 | Header Menu Footer Options | UAT | Functional | 1. Click on 'Privacy Policy' Footer link | User should be taken to 'Privacy Policy' page and proper text/information should be displayed on this page | Page Text is not displayed in this page
Defect_18 | Terms & Conditions' Footer link | Purnima | 2025-03-12 |  | Major | P0(High) | open | Version 1.1 | Header Menu Footer Options | UAT | Functional | 1. Click on 'Terms & Conditions' Footer link | User should be taken to 'Terms & Conditions' page and proper text/information should be displayed on this page | Page Text is not displayed in this page
Defect_19 | A blank 'Contact Us' page is displayed on submitting the form in 'Contact Us' page | Purnima | 2025-03-12 |  | Major | P0(High) | open | Version 1.1 | Contact Us | UAT | Functional | 1. Open Application URL 2. Click on 'Contact Us' footer option 3. Enter the details into 'Your Name', 'E-Mail Address' and 'Enquiry' fields in the 'Contact Us' page 4. Click on 'Submit' button | Success Message with text - 'Your Enquiry has been Submitted!' should be displayed in the 'Contact Us' page | A blank 'Contact Us' page is getting displayed as shown in the attached screenshot